## Project Scheduling
Project Scheduling
This report shows a sample of project scheduling using a gantt chart.
Design
| Task name |  | Start | End |  |  | Days
|  |  | 2007-02-01 | 2007-02-08
7
|  |  | 2007-02-08 | 2007-02-15
7
|  |  | 2007-02-16 | 2007-02-28
12
|  |  | 2007-03-01 | 2007-03-12
11
|  |  | 2007-03-13 | 2007-03-17
4
|  |  | 2007-03-18 | 2007-03-20
2
Statistics:
Tasks sorted by their effort
43
Programming
| Task name |  | Start | End |  |  | Days
|  |  | 2007-03-21 | 2007-04-10
20
|  |  | 2007-04-11 | 2007-04-24
13
|  |  | 2007-04-25 | 2007-05-12
17
|  |  | 2007-05-13 | 2007-05-17
4
Statistics:
Tasks sorted by their effort
54
Test
| Task name |  | Start | End |  |  | Days
|  |  | 2007-05-18 | 2007-05-22
4
|  |  | 2007-05-23 | 2007-05-25
2
|  |  | 2007-05-26 | 2007-05-27
1
|  |  | 2007-05-28 | 2007-06-09
12
|  |  | 2007-06-10 | 2007-06-12
2
|  |  | 2007-06-13 | 2007-06-15
2
Statistics:
Tasks sorted by their effort
23
Page 1
© 2005-2024, i-net software GmbH
Requirements
Concept
Class design
Data structure
GUI design
Final check
Duration of current
phase:
Coding Feature
Coding DB
Coding GUI
Unit Tests
Duration of current
phase:
Build Test Plans
Review
Execute Tests
Fixing Defects
Regress Test
Deliver Beta Build
Duration of current
phase: